## Sheet1
Task name | N/A | N/A2 | Start | End | Duration | Done by | N/A4
Finish Proposal & Slides (Kayden Tan, Zhi Yi, Zheng Bo, Jeremy) |  |  | 2025-11-05 | 2025-12-12 | 37 | Kayden Tan, Zhi Yi, Zheng Bo, Jeremy
Do Homepage (Kayden Tan (Me)) |  |  | 2025-11-24 | 2026-02-07 | 75 | Kayden Tan (Me)
Do Profile page (Zheng Bo) |  |  | 2025-11-24 | 2026-02-07 | 75 | Zheng Bo
Do Game page (Zhi Yi) |  |  | 2025-11-24 | 2026-02-07 | 75 | Zhi Yi
Do Final Report & Game Demo (Kayden Tan, Zhi Yi, Zheng Bo, Jeremy) |  |  | 2026-01-12 | 2026-02-07 | 26 | Kayden Tan, Zhi Yi, Zheng Bo, Jeremy
Integrate the Scratch Projects (Kayden Tan (Me)) |  |  | 2026-01-12 | 2026-02-07 | 26 | Kayden Tan (Me)
Do Feedback page (Jeremy) |  |  | 2025-11-24 | 2026-02-07 | 75 | Jeremy